| Project Activity Log |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Learner Name |  |  | Louis Vidal |  |  | Learner number |  |  |
| Centre Name |  |  | Highgate School |  |  | Centre Number | 12610 |  |
| Unit Name |  |  | Artefact |  |  | Unit number | P304 |  |
| Teacher Assessor |  |  |  |  |  |  |  |  |
| Proposed project title |  |  |  |  |  |  |  |  |
| This form should be used to record the process of your project and be submitted as evidence with the final piece of work. You may want to discuss: - what you have done (eg, from one week to the next) - if you are working in a group, what discussions you have had - any changes that you have or will need to make to your plans - what resources you have found or hope to find - what problems you are encountering and how you are solving them - what you are going to do next |  |  |  |  |  |  |  |  |
| Date |  | Comments |  |  |  |  |  |  |
| 24/11/24 |  | I started thinking about how I wanted to approach my EPQ. I knew I wanted to do something with neural networks and image classification, but I wasn’t really sure where to begin. I spent some time reading up on other projects and exploring different ways I could tackle this. |  |  |  |  |  |  |
| 01/12/24 | I started digging into how neural networks actually classify images, especially the maths behind it. I looked at the pros and cons of using a pre-trained model versus building parts myself. I’ve decided that doing some of it from scratch will help me really get what’s going on, especially the maths. |  |  |  |  |  |  |  |
| 10/12/24 |  | I explored the basics behind neural networks using Google’s ML documentation. Linear regression stood out to me—really liked how it makes maths dynamic. I’ve started keeping track of key formulas and ideas in Notion so I can refer back to them later. Notion is a very useful notes app with multiple functionalities especially being able to upload files from ipad from which I have written notes using a stylus. |  |  |  |  |  |  |
| 14/12/24 |  | This week I tried to properly understand how gradients work and how they’re used for optimisation. I worked through gradient descent examples manually to get the logic. I also saved a few good resources and papers into Zotero for future reference. |  |  |  |  |  |  |
| 22/12/24 |  | I explored activation functions like sigmoid, ReLU and Softmax. These are key for giving models non-linearity. I’ve now settled on trying out both CNNs and MLPs, mainly so I can compare performance. |  |  |  |  |  |  |

| 25/12/24 | Looked for datasets and decided not to create my own because of the time it’d take. Started sketching out my model structure, including number of layers and activation functions. Anything that seemed useful, I either saved to Zotero or took notes in Notion. |
| --- | --- |
| 05/01/25 | I spent time comparing MLPs and CNNs and watched some solid content like 3Blue1Brown’s neural network video. I also checked a few academic papers on Google Scholar. Stored them in Zotero so I could easily cite them later. |
| 12/01/25 | Set up my coding environment using VS Code and Jupyter. Installed CUDA drivers for the GPU and loaded the dataset. Created a workspace in Notion to track bugs and ideas as I go along. |
| 26/01/25 | Learned how to prepare image data for training, especially normalisation and resizing. Got familiar with pandas to manage the dataset. I’ve chosen a garbage classification dataset from Kaggle with six categories. Also started a GitHub repo to track changes and back everything up. |
| 02/02/25 | I bought a 4060 Ti GPU for training models later. I haven’t started using it yet, but I’ve set everything up for when I do. Also added some new tutorials into Notion and updated Zotero with research PDFs I’ll likely refer back to.. |
| 09/02/25 | Started learning how to implement CNNs in Python. Looked through PyTorch and TensorFlow docs, as well as some tutorial blogs. Started drafting early CNN model structures. |
| 16/02/25 | Ran into problems with the way the dataset was structured. My code couldn’t parse the labels correctly. I also saved pixel values the wrong way in a CSV. Need to restructure how the data is stored entirely. |
| 23/02/25 | Wrote the initial code for both CNN and MLP in PyTorch. Testing it using small batches to make sure everything runs. Saved working code snippets into Notion for easier access later. |
| 09/03/25 | Continued building both models and reviewed my MLP theory notes. Trying to ensure I understand each layer and what it’s doing mathematically. Updated my Notion notes with examples and formulas. |
| 16/03/25 | Focused on maths again—forward propagation and linear regression especially. Went through handwritten notes and then digitised the clean version in Notion. It’s helpful seeing it all laid out. |
| 23/03/25 | Did more debugging and rewrote some of the data loader functions. Also took a bit of time to reorganise my Zotero library . Tagged papers by topic so I can find things quicker later on. |
| 30/03/25 | Finished writing my MLP code using the Pytorch library, I have some issues running the code as my GPU is not recognised. This is an issue as training a model on CPU is much slower. I have tried reinstalling my CUDA drivers and resetting my virtual environments. |
| 6/04/25 | After a lot of trial and error, I figured out the issue: my CUDA version didn’t match the installed PyTorch version, and newer versions of Python weren’t compatible. Downgraded to Python 3.10 and reinstalled everything. Finally got my 4060 Ti working. |
| 13/04/25 | Started training my MLP again. The performance was not as good as expected. Was hitting around low accuracies making the model useless at this accuracy. Planning on increasing size of model for better accuracy but after some digging, I found out that MLPs can’t really retrieve spatial information (ie, edges and textures) as MLPs process input data linearly so relationships between all nodes are viewed equally as opposed to CNNs that look at the relationship between neighbouring pixels. |
| 20/04/25 | After running the MLP, I realised that its accuracy was far below the 60% I had anticipated given the image resolution and number of classes. This low accuracy showed me that the MLP struggles to capture the nuances in the data, likely because the features are too complex for a simple fully connected network. I still believe that optimisers like Adam and increasing the network size carefully could improve performance, but the results so far suggest that a CNN is necessary to better handle the image features. The distinct colours and shapes of classes, like cardboard’s light brown and green glass’s characteristic green, might help with classification, but the MLP alone doesn’t fully exploit these patterns. |
| 27/04/25 | I Finished writing my CNN model using PyTorch. After fixing the CUDA and version issues, it runs smoothly on my 4060 Ti GPU now. I’m planning to compare the CNN and MLP models side-by-side next week to see which performs better on accuracy and speed. I am learning about different ways to score a CNN so that I can get an idea of how it performed. I am learning abour f1-score, recall and precision and how they can show performance of model.. |
| 11/05/25 | Looked into a bit more detail on how to show output for CNN, I am learning about confusion matrix. |
| 18/05/25 | Started drafting the main sections of the EPQ, including Introduction, Background Research, and Planning. Focused on explaining the motivation for the project and early research into MLPs versus CNNs. |
| 1/06/25 | Expanded on the technical details of data preprocessing and model design. Described the challenges faced with MLPs and introduced the rationale for moving to CNNs. |
| 08/06/25 | Developed detailed explanations of the model architectures and training processes. Added results from initial experiments and explained adjustments made to improve performance. |
| 16/06/25 | Wrote about the evaluation of the CNN model, including performance metrics and analysis of results. Included tables and confusion matrices to illustrate findings and started reflecting on model limitations. Changed from google docs to latex on Overleaf. This allows me to draw diagrams better and to add equations. |
| 18/05/25 | Completed the Conclusion section, summarizing project outcomes and potential future improvements. Finalized formatting, citations, and ensured the document was cohesive and ready for submission. |